## Gantt Chart
| Action | Total Case# | Progress % |  | Start date | 2026-03-29
9 | Installation | 9 | 100% |  | Highlight | 2026-04-19
3 | Utillization Check | 6 | 50% |  | Date | 2
1 | Teaching | 7 | 14.29% |  | Complete | 🏴
0 | Basic Performance | 2 | 0%
0 | Acceptance Test | 10 | 0% | [6 empty] | Day | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13
| VOC | 0 | #VALUE! | [6 empty] | Week | 14 | 14 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 24 | 24 | 24 | 24 | 24 | 24
▼
No | Action | Category | Item | Remark | Status | Duration |  | Start Date | Complete Date | Date | Mar 31 | Apr 1 | Apr 2 | Apr 3 | Apr 4 | Apr 5 | Apr 6 | Apr 7 | Apr 8 | Apr 9 | Apr 10 | Apr 11 | Apr 12 | Apr 13 | Apr 14 | Apr 15 | Apr 16 | Apr 17 | Apr 18 | Apr 19 | Apr 20 | Apr 21 | Apr 22 | Apr 23 | Apr 24 | Apr 25 | Apr 26 | Apr 27 | Apr 28 | Apr 29 | Apr 30 | May 1 | May 2 | May 3 | May 4 | May 5 | May 6 | May 7 | May 8 | May 9 | May 10 | May 11 | May 12 | May 13 | May 14 | May 15 | May 16 | May 17 | May 18 | May 19 | May 20 | May 21 | May 22 | May 23 | May 24 | May 25 | May 26 | May 27 | May 28 | May 29 | May 30 | May 31 | Jun 1 | Jun 2 | Jun 3 | Jun 4 | Jun 5 | Jun 6 | Jun 7 | Jun 8 | Jun 9 | Jun 10 | Jun 11 | Jun 12 | Jun 13
[10 empty] | Week | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
1 | Installation | 납품 및 배치 | Samsung Display 납품 및 하차 | Park, 우리기연, 블루모션 | Completed | 1 | Plan | 2026-03-31 | 2026-03-31 | bar: Tue
[6 empty] | 1 | Action | 2026-03-31 | 2026-03-31 | bar: Tue
2 | Installation |  | Cleaning 및 Line 반입 | Park, 우리기연, 블루모션 | Completed | 1 | Plan | 2026-03-31 | 2026-03-31 | bar: Tue
[6 empty] | 1 | Action | 2026-03-31 | 2026-03-31 | bar: Tue
3 | Installation |  | AE "I" 형태 Loader 측 배치 | Park, 우리기연 | Completed | 1 | Plan | 2026-03-31 | 2026-03-31 | bar: Tue
[6 empty] | 4 | Action | 2026-03-31 | 2026-04-03 | bar: Fri
4 | Installation |  | XY stage 정위치 및 1차 Leveling(Foot) | Park, 블루모션 | Completed | 2 | Plan | 2026-03-31 | 2026-04-01 | bar: Wed
[6 empty] | 3 | Action | 2026-03-31 | 2026-04-02 | bar: Thu
5 | Installation |  | Cabinet 정위치 및 Leveling, 고정 작업 | Park, 우리기연 | Completed | 2 | Plan | 2026-03-31 | 2026-04-01 | bar: Wed
[6 empty] | 1 | Action | 2026-04-04 | 2026-04-04 | bar: Sat
6 | Installation | Set-up | AE 조립 및 Docking | Park, 우리기연 | Completed | 8 | Plan | 2026-04-01 | 2026-04-08 | bar: Wed
[6 empty] | 6 | Action | 2026-04-01 | 2026-04-06 | bar: Mon
7 | Installation |  | AE & Cabinet Cable 연결 | Park, 우리기연 | Completed | 7 | Plan | 2026-04-07 | 2026-04-13 | bar: Mon
[6 empty] | 8 | Action | 2026-04-06 | 2026-04-13 | bar: Mon
8 | Installation |  | 하부 FAN 장착 | Park, 우리기연 | Completed | 2 | Plan | 2026-04-14 | 2026-04-15 | bar: Wed
[6 empty] | 2 | Action | 2026-04-07 | 2026-04-08 | bar: Wed
9 | Installation |  | Power/Utility Hook-up | Park, 우리기연 | Completed | 1 | Plan | 2026-04-06 | 2026-04-09 | bar: Thu
[6 empty] | 4 | Action | 2026-04-06 | 2026-04-09 | bar: Thu
10 | Utillization Check |  | Power Turn On | Park | Completed | 1 | Plan | 2026-04-11 | 2026-04-11 | bar: Sat
[6 empty] | 3 | Action | 2026-04-11 | 2026-04-13 | bar: Mon
11 | Utillization Check |  | Utility Turn On | Park | Completed | 1 | Plan | 2026-04-13 | 2026-04-13 | bar: Mon
[6 empty] | 1 | Action | 2026-04-14 | 2026-04-14 | bar: Tue
12 | Utillization Check |  | I.O. Check [PC Setting] | Park | Started | 3 | Plan | 2026-04-15 | 2026-04-17
[7 empty] | Action | 2026-04-13
13 | Utillization Check |  | 공압 배선, Valve, Gauge 점검 | Park | Planned | 3 | Plan | 2026-04-15 | 2026-04-17
Action
14 | Utillization Check |  | Ionizer 및 상/하부 Fan setting | Park, 우리기연, 블루모션 | Planned | 2 | Plan | 2026-04-17 | 2026-04-18
Action
15 | Utillization Check |  | XY stage 2차 Leveling(Isolator) 및 Tuning | Park, 우리기연, 블루모션 | Completed | 2 | Plan | 2026-04-20 | 2026-04-21 | bar: Tue
[6 empty] | 1 | Action | 2026-04-16 | 2026-04-16 | bar: Thu
16 | Teaching |  | XY stage 3차 Leveling(Lift pin, Sample chuck) | Park, 블루모션 | Completed | 3 | Plan | 2026-04-21 | 2026-04-23 | bar: Thu
[6 empty] | 1 | Action | 2026-04-17 | 2026-04-17 | bar: Fri
17 | Teaching |  | XY stage 직각도 확인 및 정밀 Tuning | Park, 블루모션 | Planned | 5 | Plan | 2026-04-23 | 2026-04-27
Action
18 | Teaching |  | XEA(Main Program)로 각 모션부 구동 확인 및 조치 | Park, 블루모션 | Planned | 3 | Plan | 2026-04-27 | 2026-04-29
Action
19 | Basic Performance |  | XY stage clamp(aligner) setting [Glass 제공 필요] | Park, 블루모션 | Planned | 2 | Plan | 2026-04-29 | 2026-04-30
Action
20 | Teaching |  | AFM ↔ Index teaching [Loader 업체 일정 확인 필요] | Park | Planned | 1 | Plan | 2026-04-30 | 2026-04-30
Action
21 | Teaching |  | Z, F stage & Tip Scanning Head setting | Park | Planned | 3 | Plan | 2026-04-30 | 2026-05-02
Action
22 | Teaching |  | System calibration(ATX, Stage cal., ON-OFF axis cal., etc…) | Park | Planned | 5 | Plan | 2026-05-04 | 2026-05-08
Action
23 | Teaching |  | System noise 평가 및 조치 | Park | Planned | 13 | Plan | 2026-05-04 | 2026-05-16
Action
24 | Basic Performance |  | Glass 반송 평가 [야간] | Park | Planned | 17 | Plan | 2026-04-30 | 2026-05-16
Action
25 | Acceptance Test | 평가 | Manual 측정 및 자동화 측정 평가 | Park | Planned | 30 | Plan | 2026-05-18 | 2026-06-16
Action
26 | Acceptance Test |  | Sample chuck 교체(일정 변동 가능) | Park | Planned | 7 | Plan | 2026-06-18 | 2026-06-24
Action
27 | Acceptance Test |  | 설비 검수 [SDC 일정 확인 필요] | Park | Planned | 5 | Plan
Action
28 | Acceptance Test |  | SAT 항목 평가 및 문서 작성 | Park | Planned | 8 | Plan
Action
29 | Acceptance Test |  | 양산 Glass 측정 및 트러블 대응 | Park | Planned |  | Plan
Action
30 | Acceptance Test |  |  | Park | Planned |  | Plan
Action
31 | Acceptance Test |  |  | Park | Planned |  | Plan
Action
32 | Acceptance Test |  |  | Park | Planned |  | Plan
Action
33 | Acceptance Test |  |  | Park | Planned |  | Plan
Action
34 | Acceptance Test |  |  | Park | Planned |  | Plan
Action
35 |  |  |  |  | Planned |  | Plan
Action
36 |  |  |  |  | Planned |  | Plan
Action
37 |  |  |  |  | Planned |  | Plan
Action
38 |  |  |  |  | Planned |  | Plan
Action
39 |  |  |  |  | Planned |  | Plan
Action
40 |  |  |  |  | Planned |  | Plan
Action
Note on B4: Safety Automation E84 EFEM Etc.
Note on H4: Ethan.Lee: 수치 입력 시 우측 날짜 스크롤
Note on B5: Robot Teaching ATX Auto Focus Wafer
Note on B6: Calibration VLSI Stability
Note on B8: Not Included progress chart in passdown
Note on H12: Ethan.Lee: 예정 기간 입력 시 Complete Data 자동 계산 1일 기준 = 1 ex) 1월 1일 ~ 2일 = 2